## Sheet1
cost estimate for collaboration peer-teaching system
Prepared by: Hazem Hamada Abdellatif, 16p3100
Note: software development cost estimation in sheet2
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total | start Date
WBS Items
1. initiation |  |  |  | 596500 | 17.98% | 2019-01-01
summerize the needed system features | 960 | 100 | 96000 |  |  | 2019-01-01
define the system contents | 1920 | 75 | 144000 |  |  | 2019-01-02
review past lessons learned | 100 | 100 | 10000 |  |  | 2019-01-04
develop business case | 100 | 100 | 10000 |  |  | 2019-01-04
project statement of work | 900 | 50 | 45000 |  |  | 2019-01-09
Develop Project Charter. | 500 | 100 | 50000 |  |  | 2019-01-12
Determine project scope. | 400 | 100 | 40000 |  |  | 2019-01-15
Determine major Milestones. | 800 | 200 | 160000 |  |  | 2019-01-16
Identify stakeholders and sponsors. | 900 | 35 | 31500 |  |  | 2019-01-17
Assemble Project Teams, and define roles. | 100 | 100 | 10000 |  |  | 2019-01-18
2. planning |  |  | 0 | 790000 | 23.81% | 2019-01-20
Create team contract. | 300 | 200 | 60000 |  |  | 2019-01-20
Develop the scope statement | 100 | 100 | 10000 |  |  | 2019-01-25
Create WBS. | 500 | 100 | 50000 |  |  | 2019-01-29
Create budget and cost estimation. | 800 | 200 | 160000 |  |  | 2019-02-07
Prepare schedule. | 700 | 300 | 210000 |  |  | 2019-02-09
identify system needs | 400 | 200 | 80000 |  |  | 2019-02-11
Develop risk analysis. | 600 | 100 | 60000 |  |  | 2019-02-15
Document Expectations. | 300 | 300 | 90000 |  |  | 2019-02-18
Develop management plane. | 700 | 100 | 70000 |  |  | 2019-02-18
3. execution |  |  |  | 581100 | 17.52% | 2019-02-20
Content management system(CMS). | 100 | 200 | 20000 |  |  | 2019-02-20
templets and tools | 118 | 100 | 11800 |  |  | 2019-03-01
system design | 200 | 200 | 40000 |  |  | 2019-03-05
System construction. | 599 | 500 | 299500 |  |  | 2019-05-01
Implementing design. | 190 | 100 | 19000 |  |  | 2019-06-01
Measure project benefits. | 140 | 200 | 28000 |  |  | 2019-07-10
Develop system security. | 137 | 400 | 54800 |  |  | 2019-07-11
Integrate system components | 120 | 900 | 108000 |  |  | 2019-07-15
4. deployment |  |  |  | 420000 | 12.66% | 2019-08-01
Deploy the system software on the hardware. | 900 | 200 | 180000 |  |  | 2019-08-01
Deploy the system on the provided network (internet). | 500 | 200 | 100000 |  |  | 2019-08-07
Rollout. | 700 | 200 | 140000 |  |  | 2019-08-10
5. controlling |  |  |  | 445000 | 13.41% | 2019-01-01
Staff status meetings. | 100 | 100 | 10000 |  |  | 2019-01-02
Stakeholders statues reports. | 200 | 200 | 40000 |  |  | 2019-01-03
Implement integrated change control. | 50 | 100 | 5000 |  |  | 2019-01-04
Execute specific changes control plane. | 100 | 300 | 30000 |  |  | 2019-01-05
Measure and report performance. | 800 | 100 | 80000 |  |  | 2019-01-06
Monitor project variance. | 500 | 200 | 100000 |  |  | 2019-01-07
Testing. | 900 | 50 | 45000 |  |  | 2019-01-08
Fix defects found in testing stage. | 700 | 100 | 70000 |  |  | 2019-01-09
Training. | 500 | 100 | 50000 |  |  | 2019-01-10
Documentation. | 300 | 50 | 15000 |  |  | 2019-01-11
6. clossing |  |  |  | 485000 | 14.62% | 2019-03-01
Review and accept project results and customer acceptance. | 200 | 100 | 20000 |  |  | 2019-08-02
Evaluate results. | 200 | 200 | 40000 |  |  | 2019-03-03
Create software and hardware maintenance team. | 400 | 100 | 40000 |  |  | 2019-08-10
Update and archive all project records. | 300 | 100 | 30000 |  |  | 2019-03-05
Reassign recourses and release team. | 700 | 400 | 280000 |  |  | 2019-03-01
Make lessons learned report. | 200 | 300 | 60000 |  |  | 2019-08-21
Get project sponsor acceptance. | 300 | 50 | 15000 |  |  | 2019-08-23
|  |  | total: | 3317600 |  | 2019-08-20

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898