## Sheet1
Risk Register for collaboration beer-teaching system
Prepared by: Hazem Hamada Abellatif, 16p3100
No. | Rank | Risk | Description | Category | Root Cause | Potential Responses | Risk Owner | Probability | Impact | Status
1 | moderate | Insufficient QA time to validate on all browsers and OS types. | no enough time for configuration testing | technical/Performance/Quality | under estimating the schedule | extend the time for validation | project manager | 45% | no configuration testing | potential
2 | moderate | Lack of verifiable sample data | Lack of verifiable sample data | project/quality | bad planing | searching for more verifiable sample data. | prject manager | 35% | may affect the ability of the primary external stakeholder to validate end product. | monitoring
3 | low | Inadequate staff available from external stakeholders until very late in cycle. | Inadequate staff available from external stakeholders until very late in cycle. | project/quality | bad planing from stakeholders | no response | stakeholders | 25% | extend the development time and lack of stakeholders commitent | potential
4 | moderate | Following end-user testing, more effort on the user guide may be necessary. | the uer see the system is hard to use , so effort must be increased in user guide | technical | bad product technical design(UX/UI) | more effort on the user guide and validating it | team manager | 25% | more effort, the user will see the system hard to use | monitoring
5 | high | Backup and restore requires 3rd-party solutions (not evaluated yet). | not available 3rd oarty solutions for backup and restoring the data | technical/Performance/Quality/cost | no evaluated 3rd party programs yet | rent the license of the third party solutions for small period of time | team manager, project manager | 20% | no backup would be done, so any data loss wouldn't be restored | eliminated
6 | high | Insufficient time for external stakeholders to submit feedback on layout and composition of reports. | Insufficient time for external stakeholders to submit feedback on layout and composition of reports. | process/schedule | bag time planning | request for expanding the schedule | project manager | 10% | no acceptance from the stakeholders, no leasons learned | potential